Invitation for Expression of Interest

Project Name: Creative Development, Design and Fabrication, and Project Management of the Creative Placemaking of Design District Hong Kong (#ddHK)

Date: 10 May 2018

Project Brief

Design District Hong Kong (#ddHK), a creative tourism project, offering an authentic experience to tourists, blending HK’s creativity with the rich history, genuine local culture and the communities.

In the theme of “Connected city: HK stories & communities”, a series of creative works, placemaking and events will take place to infuse WanChai with creativity and telling the fascinating stories of Hong Kong. We are now launching a selection procedure to appoint the Creative Placemaking Service Provider to carry out the assignment of curate and develop, design and fabricate, manage and follow up the Creative Placemaking works.

Creative Placemaking Project

Aiming to revitalise Wan Chai District and activate the underused public space, 6 types of venues* (listed in Appendix I) in Wan Chai district may potentially be the pilot sites to implement creative placemaking ideas, not only to support art & design on streets, but more importantly, to improve neighbourhood through site-specific ideas like art on streets, installations, temporary street furniture, greenery, low-cost designs etc., in a site specific expression and the identification of the district.

In addition, creative programme such as outdoor games, performances, workshops, exhibition, education programme or public activities to activate the public space and connect with the communities are expected as a complementary part of the creative placemaking project.

* The suggested venues in Appendix I are potential venues to implement #ddHK Creative Placemaking in project year 2018. HKDC will lead the liaison with the government departments on the right to implement creative placemaking ideas on those potential venues, however, the final list of available venues are subject to change. The awarded tenderer shall assist Hong Kong Design Centre to liaise with the government departments during the project period.

Scope of the assignment including but not limited to the following:

- Curate and develop all creative placemaking works with theme and research backup to revitalise Wan Chai and activate the public space;

- Line up and develop with professional collaborators such as architect(s), urban planner(s), designer(s), artist(s), public space specialist(s), cultural experts etc., to diversify and enrich the creative placemaking works;

- Supervise and manage appointed collaborators and contractor(s) to organise, design, fabricate and execute (include installation, maintenance and dismantle) the creative placemaking works in a professional manner;

- Provide curatorial and design direction, as well as technical support to the appointed collaborators to realise all works;

- Provide detailed drawings, plans and all necessary documents for approval, and for the appointed contractor(s) to carry out the fabrication and execution.

- Coordinate and co-develop the project with Hong Kong Design Centre, #ddHK steering committee and key stakeholders of Wan Chai District

- Conduct maintenance (min. twice annually in the maintenance & defects liability period);

- Dismantle all creative placemaking works after the defined period and reinstate the venue (with acceptance) from the related government departments or venue owner/ management parties;

- Monitor & Control Quality of all fabrication & installation works, perform Site-Check after installation, maintenance and reinstatement, as well as to ensure on-time completion of all creative placemaking works;

- Organise creative activities as a complementary part of the creative placemaking project for visitors to enjoy the placemaking works;

- Report to Hong Kong Design Centre and the steering committee (With members comprise representatives of HKDC, Tourism Commission, Wan Chai District Council, Creative Industry) the project progress on a regular basis

- Assist HKDC to obtain feedback and KPI for reporting purpose;

- Perform administration tasks required throughout the project including periodical report, expenses (audited) report, meeting minutes etc.

- To deliver the above said project within the defined budget and schedule.

Tentative Project Period:

From June 2018 to March 2021 (Curate, develop, design, production and delivery of all creative placemaking works shall be completed by year end of 2018, thereafter is the maintenance & defects liability period)

Total budget of the proposal (all inclusive) – Max. HK$ 3,400,000. Deadline for EOI – 5pm on 30 May 2018.

With the goal to establish WanChai into the first Design District of Hong Kong. #ddHK aims to engage the local creative communities, organisations, experts to co-create WanChai and showcase the authentic local creativity via different creative approaches and media. Tenderer is required to submit EOI, a set of documents including a preliminary proposal of project content and collaborators’ line-up (Designers/ Artists/ Architects/ Public Space Specialist etc.). The submitted materials will be used for 1st round vetting to shortlist tenderers to further develop their proposals and enter the final round of vetting. The budget shall covers all expenses incurred to realise the proposal. Expected expenses shall include but not limited to curatorship, artist fee, royalty fee, manpower, materials, equipment rental, production, fabrication, installation & maintenance (min. twice annually in the maintenance & defects liability period), dismantle & reinstatement, transportation, insurance, certificates and safety documents, as well as all expenses incurred by organizing the creative activities. An estimated budget allocation in (FORM A) shall be filled as a compulsory part of the EOI. HKDC reserves the right to make the final decision to assign the total project budget to the awarded tenderer according to the agreed final proposal.

Hong Kong Design Centre (HKDC) will not accept double funding (apply to both public and private funding source) for the same cost item in the project, unless the ownership of the proposal and the whole project solely belongs and owns by HKDC. In case tenderer receive extra funding from public or private funding source to execute additional activities or expand the scale of the original activities, tenderer is obligated to report and seek approval from HKDC with a written statement clearly stated the allocation of the extra funding and the respective percentage of the extra funding to the original budget in that cost item. In any case, HKDC shall be the sole owner of the whole project.

The preliminary proposal in EOI should comply with:

- The Laws and the Basic Law of HKSAR of the People’s Republic of China

- The goal of the project to develop WanChai into Design District of Hong Kong

- The realities of site-specific works/ activities in particular place suggested (stated in Appendix I)

- The audience which is targeted, as numbers and type

- The ordinance on public order and security

Who can participate?

- Individual Applicant

- Permanent Resident of HKSAR

- Aged 18 or above

- Architects, Urban Planners, Designers, Artists, Craftsmen, Engineers, Art Educator, Cultural specialist or in related professions

- Legal Entity

- Legal organisation, group, association or business based in Hong Kong

- Hong Kong registered with effective Business Registration/ or with equivalent certificate and document/ or with office bearers/ or with legal representatives

The implementation of the above stated requirements is certified by a declaration which is an integral part of the EOI. The detailed conditions and obligations of the tender are subject of the contract that the awarded tenderer signs with Hong Kong Design Centre on the basis of the Laws and the Basic Law of HKSAR of the People’s Republic of China and in accordance with the suggestion the jury had made.

Selection Process

Stage 1 – Expression of Interest (EOI)

Interested party shall submit EOI (FORM A, FORM B and FORM C) as specified in submission requirements to Hong Kong Design Centre office by 5pm on 30 May 2018. A Jury panel will have 1st round vetting to shortlist max. 5 tenderers (Tentatively by 4 June 2018) to enter stage 2 for final proposal. The shortlisted tenderers will receive an email notification issued by the Hong Kong Design Centre as confirmation.

Stage 2 – Final proposal

The shortlisted tenderers shall develop and submit the final proposal and the related budget breakdown by 5pm 29 June 2018. All shortlisted tenderers will be invited to a vetting presentation (tentatively on or before 4 July 2018). Announcement of the tender result will be published on HKDC website, and the awarded tenderer will receive an email notification from HKDC in early July 2018 for confirmation. HKDC shall pay each shortlisted a pitching fee at a sum of HK$20,000 who is considered unsuccessful by HKDC in the vetting process of Stage 2 on a gratuitous basis. However, HKDC reserves the right not to pay any tenderer with incomplete submission of documents and no show-up at presentation.

HKDC shall have no obligations whatsoever to accept the proposal with lowest price or to accept any proposal at all.

A Jury will be formed by minimum of 3 Board of Directors, Executive Director and Senior Management of Hong Kong Design Centre and representative of #ddHK project steering committee. The final formation of jury members is subject to change without prior notice to tenderer.

Assessment Criteria

| Curatorial Direction in response to #ddHK project aims & annual theme - Expression of specific characteristics, history and contemporary life of WanChai - Contribution to the transformation of WanChai into design district - Contribution to attracting new audience such as international tourists - Strategy to reach efficient publicity | 20% |
| --- | --- |
| Content & Collaborators line-up - Variety of creative approaches, activities and collaborators line-up - Originality of proposal/ Innovativeness/ Artistic value/ Standard of design excellence - Allows community inclusiveness and diversity - Contribution to the ambiance and current lives in the district | 30% |
| Creative Portfolio/ Past Experience & Team Structure - Relevance of past project experience as #ddHK - High level of creativity and execution ability - Flexibility to co-develop the project proposal with #ddHK’s key stakeholders - Placemaking related expertise and support of the project team (min. 80% team members are practicing creative professionals) | 30% |
| Budget Allocation - High percentage of budget used to realise the project - The logistical and financial viability of the proposal as presented in the draft breakdown of costings and budget allocation for each of the proposed components | 20% |

Submission Timeline

| Date | Submission |
| --- | --- |
| 30 May 2018 by 5pm | Expression of Interest (EOI) |
| 29 June 2018 by 5pm | Final proposal (shortlisted tenderers only) |
| By end Jul 2018 | Finalised final proposal (Awarded tenderer only) |

Key Date (Tentative)

| Date | Description |
| --- | --- |
| 17 May 2018 at 5pm | Briefing session* @ HKDC office |
| 30 May 2018 by 5pm | Submission deadline of EOI |
| By 4 June 2018 | 1st Round Vetting |
| By 5 June 2018 | Announcement of shortlisted tenderers (Shortlisted tenderers will receive an email notification) |
| 5 June – 29 June 2018 | Shortlisted tenderers to develop final proposal** |
| 29 June 2018 by 5pm | Submission of final proposal (shortlisted tenderers only) |
| On or before 4 July 2018 | 2nd Round Vetting: Vetting Presentation of final proposal |
| Early Jul 2018 | Announcement of awarded tenderer (Shortlisted tenderers will receive an email notification) |
| Jul 2018 | Finalise final proposal (Awarded tenderer only) |
| By end Jul 2018 | Submission of revised final proposal (Awarded tenderer only) |
| Aug 2018 onwards | Production & Execution of creative placemaking works, Submission of required doc. & cert. |
| Sep 2018 | Commence of 1st lot of creative placemaking |
| By end Nov 2018 | Completion and delivery of all creative placemaking |

*HKDC will only arrange one briefing session for this creative placemaking project. All interested tendered shall email to meiping.lam@hkdesigncentre.org by 12 noon of 16 May 2018 on the attendance to the briefing session.

**Remarks: The revised final proposal (submission by end Jul 2018) shall remind minimum 70% as of the submitted final proposal (submission for 2nd Round Vetting). Change of content or collaborators line-up and their respective budget with more than 70% of the submitted original final proposal shall seek for HKDC’s prior approval via official written letter with full proposal and justification at least two weeks before the submission deadline of revised final proposal. If HKDC do not approve the related changes, HKDC reserves the right to disqualify the awarded tenderer or withdraw the tender.

List of Required Documents

- Completed EOI (FORM A, B & C)*

- For individual applicant: 
a) scanned copy of HKID card*;
b) CV, Creative portfolio, Reference of Past Projects of the tenderer*.

- For legal entity: 
a) scanned copy of the effective Business Registration Certificate (BR) registered in Hong Kong / equivalent document obtained in Hong Kong certifying the actual status of the entity / Name list of the office bearers or legal representatives of the entity*;
b) CV of the office bearers or legal representatives*;
c) CV of the project curator, project in charge, project manager and the creative team*;
d) Creative portfolio, Reference of Past Projects of the tenderer*.

- Partnership statement letters (if applicable)

- Graphic and video materials, presenting the proposal– visualizations, pictures, etc.  (maximum 5 pages of A4 and 2 videos if applicable)

The documents marked with " * “ are obligatory. EOI missing any one of the obligatory documents will not be considered.

Submission Requirements

- The EOI (Form A, B & C) should be completed and submitted as required form of the template with signature of the tenderer/ office bearer/ legal representative along with company chop (for Legal Entity only). The full package of EOI should be submitted in both hard copies (6 copies) and soft copies in pdf format (recorded in CD or DVD). The envelope should be marked: “EOI: #ddHK Creative Placemaking 2018 <NAME OF TENDERER>”.

- The full package of EOI (as listed in the “List of required documents”) shall reach Hong Kong Design Centre (address and office hour listed as below) by 5pm on 30 May 2018 in sealed envelopes as specified above. Submission by Fax/ Email will not be accepted. Late submission will not be considered.

Hong Kong Design Centre

1/F Innocentre, 72 Tat Chee Ave., Kowloon Tong, Hong Kong

Office Hour: Monday to Friday, from 9 am – 12:30 pm and 1:30 pm  to 6 pm)

- Permitted file formats in the soft copies are: .doc, .docx, .ppt, .xls, .xlsx, .pdf; additional audio-visual aids materials: .jpg, .jpeg, .png, .mov, .avi, .mp3, .mp4, .wav. All other formats will not be considered.

- One envelope should contain one EOI only.

Contact

For further enquiry, please contact

Ms. Meiping Lam

Project Manager

Hong Kong Design Centre

Email: meiping.lam@hkdesigncentre.org/ Tel: +852 3793 8432

General:

This ‘Expression of Interest is both confidential and proprietary to Hong Kong Design Centre (HKDC). HKDC reserves the right to recall the ‘Expression of Interest’ in its entirety or in part. 

The tenderer shall not include or reference this ‘Expression of Interest’ in any publicity without prior written approval from HKDC. The tenderer accept all of the foregoing terms and conditions without exception. All responses to the ‘Expression of Interest’ will become the property of HKDC and will not be returned.

If there is any inconsistency or ambiguity between the English version and the Chinese version, the English version shall prevail. All matters and disputes will be subject to the final decision of Hong Kong Design Centre.

Conflict of Interest:

Shortlisted tenderer (from the stage 1 vetting) and their key project team members shall declare conflict of interest before the stage 2 vetting. In general, the tenderer and their key project team members (including but not limited to the individual tenderer, the office-bearer, the legal representative, owner, shareholders, board of directors, employees and staff of the legal entity) shall declare their conflict of interest if they perform a function in Hong Kong Design Centre.

Disclaimer:

Whilst the information in this invitation document has been prepared in good faith, it does not claim to be comprehensive or has been independently verified. Any liability in respect of any such information or inaccuracy in or omission is expressly disclaimed. Hong Kong Design Centre is not obliged to inform tenderers of any update or change of any of the information in the Invitation Document made or that comes to its knowledge after the issue of the Invitation Document.